## DP (hidden)
Delivery Point | Direction
Achim II | Exit
Alekseevka | Entry
Arnoldstein | flange
Bacton | injection
Baumgarten | withdrawal
WAG Baumgarten
Beregovo
Bergermeer
Bobbau
Brandov
Brandov-GASPOOL
Brandov-Opal
Caushany
IP Brandov
IP Brandov-Opal
VIP-Brandov-GASPOOL
Bunde
Deutchneudorf
Deutschneudorf - HSK
Deutschneudorf EUGAL
Drohne
Drozdovychi
Ellund
Eynatten
GASPOOL
VIP-TTF-GASPOOL-H
Gernsheim
Grebeniki
Greifswald
Greifswald-NEL
Greifswald-OPAL
Horgos
Julianadorp
Kienbaum
Kiskundorozsma
Kobrin - Vysokoe
Kondratki
Lanzhot
Lubmin II
Mallnow
Medelsheim
NCG
Obergailbach/Medelsheim
Oberkappel
Oberkappel VIP
Olbernhau
Olbernhau II
Olbernhau/HSK-Saida
Orlovka
Oude Statenzijl
Portovaya
Ronneburg
Slavyanskaya
Smolensk-Kondratki
Sokhranovka
Steinitz
Sudzha
TTF
VIP-TTF-NCG-H
Überackern ABG
Überackern II
Überackern SUDAL
Überackern ABG/SUDAL
Überackern Südal - Überackern ABG/Überackern Südal
UGS Banatski Dvor
UGS Bergermeer
UGS Damboѓіce
UGS Haidach
Haiming 3-Haidach
UGS Katharina
UGS Nafta
UGS Rehden
Sp. Rehden
Uzhgorod
Velke Kapusany
VIPBENE
VTP Austria
VTP Hungary
VTP Slovakia
VTТ Croatia
VIP Waidhaus
Waidhaus
Zee Beach
Zelzate
Zvornik

## rus_eng 2026
Proposed Maintenance Program for the "Transportgas Srbija" Gas Transmission System for 2027
№ | Company performing maintenance | CS/GMS/UGS | Direction | ID TSO work | Start date | Start time, CET | Completion date | Completion time, CET | Duration, hours | Duration, days | Maximum available capacity, mln. m³/d (20⁰ C) | Max. reduction % | Note
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | PE “Srbijagas”, Novi Sad | GMS Horgoš 1 (old gas station) | Entry | Connecting a new two-way gas station to gas pipelines MG-06 and MG-07 | 2027-04-05 | 06:00:00, CEST | 2027-04-07 | 06:00:00, CEST | 48 | 2 | 0 | 100%
2 | PE “Srbijagas”, Novi Sad | PSG Banatski Dvor | withdrawal | Connecting a new two-way gas station to gas pipelines DV-04-18 | 2027-04-14 | 06:00:00, CEST | 2027-04-16 | 06:00:00, CEST | 48 | 2 | 0 | 100%
3 | PE “Srbijagas”, Novi Sad | PSG Banatski Dvor | injection | Connecting a new two-way gas station to gas pipelines DV-04-18 | 2027-04-14 | 06:00:00, CEST | 2027-04-16 | 06:00:00, CEST | 48 | 2 | 0 | 100%
4 | PE “Srbijagas”, Novi Sad | GMRS Ćuprija, GMRS Popovac i GMRS Paraćin | Exit | Relocation of gas pipelines MG-08 + GMRS Ćuprija 2 | 2027-04-14 | 00:00:00, CEST | 2027-04-15 | 23:55:00, CEST | 48 | 2 | 0 | 100%
5 | PE “Srbijagas”, Novi Sad | There is no suspension to users of the system | Exit | Relocating the gas pipeline RG-01-10 under the Danube River | 2027-05-03 | 00:00:00, CEST | 2027-05-05 | 23:055:00, CEST | 48 | 2 | 100 | 0%
6 | PE “Srbijagas”, Novi Sad | GMRS Gitarić, GMRS Požarevac | Exit | Relocation of the gas pipeline RG 08-01 (GRČ „Veliko Orašje“ – GMRS „Radinac“) due to the construction of the state road IV line Loop "Požarevac" - Požarevac (Bypass) | 2027-05-10 | 00:00:00, CEST | 2027-05-11 | 23:055:00, CEST | 48 | 2 | 0 | 100%
7 | PE “Srbijagas”, Novi Sad | There is no suspension to users of the system | Exit | Relocation of gas pipelines RG 08-02 (Section GRČ Bresnica - GRČ Kraljevo) on the Morava Corridor SECTOR 3 ADRANI - PRELJINA | 2027-05-17 | 00:00:00, CEST | 2027-05-18 | 23:55:00, CEST | 48 | 2 | 100 | 0%
8 | PE “Srbijagas”, Novi Sad | There is no suspension to users of the system | Exit | Relocation of gas pipelines RG 09-04 (GRČ Pojate - GRČ Kruševac) on the Morava Corridor SECTOR 3 ADRANI - PRELJINA | 2027-05-25 | 00:00:00, CEST | 2027-05-26 | 23:55:00, CEST | 48 | 2 | 100 | 0%
9 | PE “Srbijagas”, Novi Sad | PPS Zvornik (IP Loznica) | Exit | Connecting a new two-way gas station to gas pipelines RG-05-04 | 2027-06-02 | 06:00:00, CEST | 2027-06-03 | 06:00:00, CEST | 24 | 1 | 0 | 100%
LLC Transportgas Srbija
Novi Sad, oktobar 2026.
INFO
You can send all proposals and suggestions for the Maintenance Program proposal until 01.12.2026. years to mail: info@transportgas-srbija.com