Draft Maintenance Program on the Gas Transmission System "Transportgas Serbia" for 2026.

Based on the notification from the transmission system owner JP Srbijagas dated October 16, 2025, the planned dates for the replacement works of sectional valves with actuators are carried out according to the schedule provided in the table.

| Shutdown zone | Work site | Entry point | Exit point | Customer / Trader | Work start date | Work end date | Remaining capacity (m³/h) | Remaining capacity (%) | NOTE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Zona 11 | Gas pipeline RG-04-15 At GRS Gospođinci (station 00+000) | Gas pipeline RG-04-15, section GRČ Gospođinci – BV Srbobran | GMRS Temerin GMRS Srbobran GMRS Pionir Srbobran GMRS SGS Srbobran | Supplier: JP Srbijagas, NIS Distributor: JP Srbijagas, Gas Temerin, Vrbasgas, Somborgas End customer: Pionir Srbobran, NIS (SGS Srbobran) | 21.04.2026. | 24.04.2026. | 0 | 0% | Replacement and removal of five (5) valves with actuator replacement at GRČ Gospođinci. During the works, there will be a complete interruption of gas transport through the section. The listed exit points will certainly be without gas. Depending on the consumption in the blocked section BV Srbobran (station 26+512) – GMRS Sombor (station 84+292), the following may also be without gas: GMRS Bačko Dobro Polje, GMRS Vrbas, GMRS Kula, GMRS Odžaci, GMRS Ruski Krstur, GMRS Crvenka, GMRS Sivac, GMRS Apatin, GMRS Kljaijićevo, and GMRS Sombor. |
| Zona 9-1 | Gas pipeline MG-04/2: GRČ Gospođinci (station 59+154) Block station Beška (station 80+800) | GMS 4 in Gospođinci, Gas pipeline MG-04/II Gospođinci – Batajnica | GMRS Budisava GMRS CHP Novi Sad GMRS Šajkaš GMRS Vilovo | Supplier: JP Srbijagas Distributor: JP Srbijagas, Novi Sad-Gas End customer: Panonske CHP (CHP Novi Sad) | 11.05.2026. | 15.05.2026. | 0 | 0% | Replacement and removal of eight (8) valves with actuator replacement on the gas pipeline MG-04/II. During the works, there will be a complete interruption of gas transport through the section. It is necessary to construct a bypass line at GRČ Gospođinci. |
| Zona 8-3 | GRČ Gospođinci | GMS 4 at the Gospođinci junction | Bidirectional gas pipeline DV 04-17 Gospođinci – B. Dvor | Supplier: JP Srbijagas Gazprom | 25.05.2026. | 29.05.2026. | 0 | 0% | Replacement-cutting of six (6) valves with actuator replacement in the Gospođinci hub. During the works there will be a reduction in gas delivery from the Gastrans d.o.o. pipeline to GMS 4 in Gospođinci and a complete interruption of gas injection into the PGS B. Dvor via the bidirectional pipeline DV 04-17 Gospođinci-B. Dvor. |
| Zona 14-1 | Gas pipeline RG-05-04/I from OČS at GRČ Batajnica (station 00+000) to PČS at GRČ Šabac (station 67+537) | Gas pipeline RG-05-04 | GMRS Luk Loznica GMRS Lešnica GMRS Duvanište GMRS Šabac 1 GMRS Šabac 2 | Supplier: JP Srbijagas, Gazprom TSO: Gaspromet Pale Distributor: Loznica-Gas, JP Srbijagas, JKP Toplana Šabac End customer: Duvanište | 16.06.2026. | 18.06.2026. | 0% | 0% | Replacement and removal of three (3) valves with actuator replacement on the gas pipeline RG-05-04/I. During the works, there will be a complete interruption of gas transport through the section. |
| Zona 19 | Gas pipeline MG-08 BV Lanište (station 41+800) BV Left bank of the Great Morava (station 58+330) BV Right bank of the Great Morava (station 58+636) | Gas pipeline MG-08 | GMRS Markovac GMRS Markovac 2 GMRS Svilajnac GMRS Lapovo GMRS Lapovo 2 GMRS Jagodina 2 GMRS Jagodina GMRS Ćuprija GMRS Paraćin GMRS Popovac | Supplier: JP Srbijagas End customer: Kronospan Moravacem | 07.07.2026. | 10.07.2026 | 0% | 0% | Replacement and removal of three (3) valves with actuator replacement on the gas pipeline MG-08. During the works, there will be a complete interruption of gas transport through the section. |
| Zona 14-2 | Gas pipeline RG-05-04/II From OČS at GRČ Šabac (station 67+537) to BV Šepak, Republic of Srpska (left bank of the Drina) (station 115+437) | Gas pipeline RG-05-04 | GMRS Luk Loznica GMRS Lešnica GMRS Duvanište GMRS Šabac 1 GMRS Šabac 2 | Supplier: JP Srbijagas, Gazprom TSO: Gaspromet Pale Distributor: Loznica-Gas, JP Srbijagas, JKP Toplana Šabac End customer: Duvanište | 28.07.2026. | 30.07.2026. | 0% | 0% | Replacement and removal of three (3) valves with actuator replacement on the gas pipeline RG-05-04/II. During the works, there will be a complete interruption of gas transport through the section. |
| Zona 16 | GRČ Pančevo, valve 620 | BRM on gas pipeline RG-04-07 | Gas pipeline MG-01 | Supplier: JP Srbijagas, NIS Distributor: JP Srbijagas End customer: Petrohemija | 02.09.2026. | 04.09.2026. | 0% | 0% | If all valves and the newly installed three MOVs at GRČ Pančevo are leak-tight, the works can be carried out without interrupting the natural gas supply to consumers. In the event that the shut-off devices are leaking, the replacement works on the specified MOV will be uncertain and relatively difficult to perform, considering that it is not known whether and when the consumers connected with NIS will be operating and consuming gas. |